## UI Audit Report
AE Group — Website UI Audit Report
Comparison: ae-group.webc.in/wp-new vs Figma Design (Node: 527-1930)
| 6 Issues | 7 Issues | 4 Issues | 17 Issues
| HIGH PRIORITY | MEDIUM PRIORITY | LOW PRIORITY | TOTAL ISSUES
# | Section | Issue Description | Priority | Recommendation | Page Location | Element / Selector | Expected (Figma) | Actual (Live Site) | Status | Assigned To
1 | Navigation | Dual logo stacking — two logo SVGs may not align as a single lockup | ● High | Use one combined SVG or apply flexbox with fixed gap to lock the icon + wordmark | Homepage — Header | .site-header .logo a (Union-2.svg + Union-1.svg) | Single horizontally-aligned logo lockup: icon + wordmark with 8px gap | Two separate <img> tags stacked — may misalign on smaller screens | Open
2 | Navigation | No active/current state indicator on nav links | ◑ Medium | Add underline or accent color to the active page nav item per Figma spec | Homepage — Header Nav | nav ul li a (active page) | Active nav link has bottom border accent in brand color | No active state class or visual indicator applied | Open
3 | Hero Section | Hero image focal point may shift on different viewport sizes | ● High | Set object-fit: cover with object-position matching Figma focal point | Homepage — Hero | .hero-section img (6.jpg) | Fixed-height hero (600px) with focal point centered on building facade | Image may crop incorrectly on mobile — no object-position set | Open
4 | Hero Section | 'About Us' CTA renders as plain text link, not a button | ● High | Apply button styles (border, padding, hover state) matching Figma design | Homepage — Hero | .hero-section .cta-button 'About Us' | Outlined button: 1px border, 14px padding H, 10px padding V, hover fill | Renders as unstyled <a> text link with no button treatment | Open
5 | About / Stats | '70+ Years' stat not displayed as a typographic callout element | ● High | Separate stat into a large display figure with label, styled per Figma | Homepage — About Section | .about-section .stat-block '70+ Years' | Large display stat: 72px bold number, 16px label below, separated from body | '70+' and 'Years' appear inline within paragraph text | Open
6 | About / Stats | 'Explore More' link lacks arrow icon or hover animation | ◑ Medium | Add arrow icon and underline/slide animation consistent with Figma | Homepage — About Section | .about-section a 'Explore More' | Text link with right arrow icon (→), underline on hover, brand color | Unstyled anchor tag — no icon, no hover animation | Open
7 | Services | Service card hover state uses same image as default — hover broken | ● High | Supply distinct hover images or implement CSS overlay per Figma hover spec | Homepage — Services Grid | .service-card:hover .card-overlay | On hover: dark overlay appears, service title slides up, arrow icon fades in | Hover image src is identical to default — no visual change on hover | Open
8 | Services | CFD Analysis, Energy Modeling, Pipe Stress cards share near-identical images | ● High | Replace with distinct, service-specific photography for each card | Homepage — Services Grid | .service-card:nth-child(3,4,5) img | Each card has a unique, service-specific photograph | Cards 3–5 use near-identical variants of img-values-1.webp placeholder | Open
9 | Services | Duplicate 'View All' CTA — appears both above and below the service grid | ◑ Medium | Remove the top instance; retain only the bottom CTA per Figma layout | Homepage — Services Section | .services-section .view-all-top (above grid) | Single 'View All' CTA below the service cards only | Duplicate 'View All' link appears both above and below the grid | Open
10 | Client Logos | Client logo strip is static grid — no marquee/scroll animation | ◑ Medium | Implement infinite horizontal scroll marquee for the logos section | Homepage — Client Logos | .clients-section .logo-strip | Infinite horizontal marquee animation, ~8s loop, pause on hover | Static grid of 8 logo images — no scroll animation | Open
11 | Client Logos | Logo sizes may be inconsistent — no uniform height constraint | ○ Low | Set max-height on all logo images and use object-fit: contain | Homepage — Client Logos | .clients-section .logo-strip img | All logos constrained to max-height: 48px, object-fit: contain | Logos may render at native image sizes causing visual inconsistency | Open
12 | Projects | Project card hover images are identical to default images (wrong src) | ● High | Correct the hover image src attributes — verify file paths in WP media library | Homepage — Projects Grid | .project-card img (hover src) | Hover state shows a different darker/cropped version of the project image | Both <img> tags reference the same src URL — hover swap non-functional | Open
13 | Projects | Category tags (e.g. 'Public / Municipal') unstyled plain text | ◑ Medium | Apply pill/tag styling with background color per Figma tag component spec | Homepage — Projects Grid | .project-card .category-tag (e.g. 'Public / Municipal') | Pill tag: bg #E8EEF8, border-radius 20px, 10px font, brand blue text | Plain unstyled text rendered above the project title, no tag styling | Open
14 | Contact Form | Submit button is missing from the contact form markup | ● High | Add a styled submit button matching Figma's 'Send Message' button spec | Homepage — Contact Form | .contact-form button[type=submit] | Filled button 'Send Message': bg brand blue, white text, full-width on mobile | No submit button element present in the form markup | Open
15 | Contact Form | Form image layout may not match Figma split-column design | ◑ Medium | Verify 50/50 column split with image flush to the edge as designed in Figma | Homepage — Contact Form | .partner-section layout (image + form) | 50/50 split: full-bleed image left column, form right column with 48px padding | Image position and column ratio may not match Figma split-column spec | Open
16 | Footer | Newsletter section contains placeholder copy unrelated to AE Group | ● High | Replace with actual brand copy about engineering updates/newsletters | Homepage — Footer | .footer .newsletter p (description text) | Copy: 'Stay updated with our latest engineering insights and project news' | Shows: 'Adapting planting and watering schedules based on AI weather predictions' | Open
17 | Footer | Social media icons absent from footer | ○ Low | Add LinkedIn (and other relevant) icon links to the footer | Homepage — Footer | .footer .social-links | LinkedIn icon + link; possibly Twitter/X — per Figma footer component | No social media icons or links present in footer | Open
18 | Typography | Section eyebrow labels use inconsistent capitalisation style | ○ Low | Standardise all eyebrow labels to one style (e.g. ALL CAPS with letter-spacing) | Homepage — All Sections | .section-eyebrow (all instances) | All eyebrow labels in ALL CAPS with letter-spacing: 0.1em, consistent style | Mixed casing: 'What we do', 'Our Clients', 'Partner with us' — inconsistent | Open
19 | Insights | Only 2 blog cards shown — grid appears unbalanced if 3-col layout | ○ Low | Add a third blog post or adjust grid to 2-column to avoid visual imbalance | Homepage — Insights Section | .insights-section .blog-grid | 3-column grid with 3 blog cards for visual balance | Only 2 blog cards shown — third column empty, layout appears incomplete | Open
Generated: April 2, 2026 ¦ Website: ae-group.webc.in/wp-new ¦ Auditor: Claude (Anthropic)